## Gantt Chart
CAPSTONE PROJECT 2 TIMELINE
PPH INTEGRATED PROCUREMENT & INVENTORY MANAGEMENT SYSTEM WITH DEMAND FORECASTING
BSIT IV-C
ACTIVITIES | JUNE 2026 |  |  |  | JULY 2026 |  |  |  | AUGUST 2026 |  |  |  | SEPTEMBER 2026 |  |  |  | OCTOBER 2026 |  |  |  | NOVEMBER 2026 |  |  |  | DECEMBER 2026
| WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1
SYSTEM DEVELOPMENT
Project Orientation & Capstone 2 Timeline Planning | bar: JUNE 2026 WEEK 1
Requirements Gathering, Analysis & Review of Capstone 1 Findings | bar: JUNE 2026 WEEK 1 to JUNE 2026 WEEK 2
System Design (Database Schema, Architecture, UI/UX) | bar: JUNE 2026 WEEK 2 to JUNE 2026 WEEK 3
Development: Authentication, Session Security & User Administration | bar: JUNE 2026 WEEK 3 to JULY 2026 WEEK 1
Development: Master Data, Inventory & Stock Ledger | bar: JULY 2026 WEEK 1 to JULY 2026 WEEK 3
Development: Batch, Expiry, Disposal & Stock Adjustment | bar: JULY 2026 WEEK 3 to JULY 2026 WEEK 4
Development: Procurement & Multi-Level Approval Workflow | bar: JULY 2026 WEEK 4 to AUGUST 2026 WEEK 2
Development: Department (Ward) Stock, Transfers & Budgets | bar: AUGUST 2026 WEEK 2 to AUGUST 2026 WEEK 3
Development: Demand Forecasting (Moving Average & Exponential Smoothing) | bar: AUGUST 2026 WEEK 3 to AUGUST 2026 WEEK 4
Development: Notifications, Real-Time Layer (SignalR) & Dashboards | bar: AUGUST 2026 WEEK 4 to SEPTEMBER 2026 WEEK 1
Development: Reports, Excel Exports & LGU Forms (RIS, PR) | bar: SEPTEMBER 2026 WEEK 1 to SEPTEMBER 2026 WEEK 2
Development: Backup & Recovery, Audit Trail & System Settings | bar: SEPTEMBER 2026 WEEK 2 to SEPTEMBER 2026 WEEK 3
System Integration & Debugging | bar: AUGUST 2026 WEEK 4 to OCTOBER 2026 WEEK 1
System Consultation with Adviser & Panel | bar: SEPTEMBER 2026 WEEK 3 to SEPTEMBER 2026 WEEK 4
PRE-FINAL DEFENSE | bar: OCTOBER 2026 WEEK 1
Usability Testing (ISO/IEC 25010 Evaluation with End Users) | bar: OCTOBER 2026 WEEK 2 to OCTOBER 2026 WEEK 3
User Acceptance Testing (UAT) per Role | bar: OCTOBER 2026 WEEK 2 to OCTOBER 2026 WEEK 3
Performance, Concurrency & Cross-Browser Testing | bar: OCTOBER 2026 WEEK 3 to OCTOBER 2026 WEEK 4
System Refinement Based on Test Results & Panel Comments | bar: OCTOBER 2026 WEEK 3 to NOVEMBER 2026 WEEK 2
Production Hardening (Secrets, CORS, SMTP, Health Monitoring) | bar: NOVEMBER 2026 WEEK 1 to NOVEMBER 2026 WEEK 2
System Finalization & Deployment Turnover | bar: NOVEMBER 2026 WEEK 2 to NOVEMBER 2026 WEEK 4
MANUSCRIPT WRITING
Chapters 1-3 Revision Based on Capstone 1 Recommendations | bar: JUNE 2026 WEEK 1 to JUNE 2026 WEEK 2
Chapter 4 Discussion (Presentation, Analysis & Interpretation of Data) | bar: JUNE 2026 WEEK 2
Chapter 5 Discussion (Summary, Conclusions & Recommendations) | bar: JUNE 2026 WEEK 3
Chapters 4 & 5 Writing | bar: JUNE 2026 WEEK 4 to OCTOBER 2026 WEEK 1
Documentation of System Output (Screenshots, Data Dictionary, Specs) | bar: AUGUST 2026 WEEK 4 to SEPTEMBER 2026 WEEK 4
Tabulation & Statistical Treatment of Usability Test Results | bar: OCTOBER 2026 WEEK 3 to OCTOBER 2026 WEEK 4
Chapters 4 & 5 Consultation | bar: OCTOBER 2026 WEEK 2 to NOVEMBER 2026 WEEK 1
Abstract, Preliminaries, CV & Other Parts Discussions | bar: OCTOBER 2026 WEEK 4 to NOVEMBER 2026 WEEK 1
Preparation for Final Defense | bar: NOVEMBER 2026 WEEK 1 to NOVEMBER 2026 WEEK 2
FINAL DEFENSE | bar: NOVEMBER 2026 WEEK 3
IMRAD Discussions | bar: NOVEMBER 2026 WEEK 4
Manuscript Revisions & Hardbound Submission | bar: NOVEMBER 2026 WEEK 4 to DECEMBER 2026 WEEK 1
LEGEND
System module development
Design, hardening & technical setup
Testing & evaluation (usability, UAT, performance)
Debugging & refinement
Manuscript writing
Consultation
Manuscript discussions & data treatment
Defense milestone
Revisions & hardbound submission
Prepared by: | AUGUST 2026 WEEK 4: Noted by:
Name | AUGUST 2026 WEEK 4: CARLA CARMELA P. RAMOS, DIT
Researcher / System Developer | AUGUST 2026 WEEK 4: Subject-in-charge